## Sheet1
Major change | Current plan | Potential benefit | Risk to historically undercounted groups | Worst-case scenario | Priority research need | Advocacy ask | Decision deadline
In-Office Enumeration | Use administrative and supplemental data to resolve some nonresponding households without completing enumeration through continued field contact. | Resolve genuinely unreachable cases; reduce poor-quality proxy responses; concentrate field resources where they add value. | People with weak administrative records may receive less direct enumeration even though their records are least reliable. | Difficult or expensive households are moved out of fieldwork early and counted through incomplete or incorrect records. | Validate IOE separately by population, geography, household type, and characteristic; assess constitutional and statutory limits. | Preserve direct response as the presumption; publish eligibility rules, contact requirements, data sources, use rates, and quality results. | Before Baseline 2 for basic rules; before the 2028 Dress Rehearsal for production design.
Person Characteristic Frame | Build and continually update a linked frame of people, addresses, household relationships, characteristics, and quality measures to support matching and enumeration. | Improve matching, identify omissions and duplicates, support IOE, and reduce repetitive data collection. | Records may be missing, outdated, or inaccurate for mobile people, young children, immigrants, complex households, and detailed racial and ethnic groups. | The PCF becomes an authoritative-looking but systematically incomplete representation of communities and household structures. | Measure differential coverage, address accuracy, household reconstruction, characteristic quality, and error propagation. | Publish source-quality assessments and intended uses; establish heightened privacy, access, and audit safeguards. | Before PCF rules drive Baseline 2 and 2028 systems.
Near real-time processing and automated resolution | Process responses, matches, anomalies, and quality signals more continuously during collection rather than primarily after operations end. | Identify problems earlier; resolve duplicates faster; redirect field resources while corrections are still possible. | Automated systems may treat less common households or response patterns as errors more frequently. | Algorithms silently resolve legitimate complexity incorrectly at scale before anyone recognizes the pattern. | Differential audits of matching, anomaly detection, duplicate resolution, and human overrides. | Require predetermined quality measures, demographic and geographic monitoring, escalation paths, and auditable decision logs. | Before 2028 Dress Rehearsal system integration.
Race and ethnicity content | Final 2030 content remains subject to Census research, statistical standards, and federal policy decisions. | Updated content can improve accuracy and representation of the nation’s population. | Political intervention or reversal of tested standards could reduce the visibility or accuracy of particular populations. | Important categories are removed or weakened without adequate research or public process, degrading census and downstream civil rights data for a decade. | Document scientific basis, testing, operational effects, and downstream uses of alternative content. | Require transparent, research-based decisions and meaningful public review before content becomes fixed. | Before questionnaire development must be stable for the 2028 Dress Rehearsal.
Language access | Baseline 1 assumes multilingual questionnaires, telephone services, translated materials, and other language support, but Commerce policy creates significant uncertainty. | Increase direct response, reduce field workload, and improve data quality among households with limited English proficiency. | Reduced language support may lower self-response and increase proxies or administrative enumeration in communities already at greater risk of being missed. | Major response channels become effectively English-only and community organizations must improvise unofficial translations. | Estimate the effects of each language service on response, cost, characteristics, and downstream fieldwork. | Preserve multilingual access across internet, telephone, paper, field, mail, and partner communications; seek formal clarification of Commerce policy. | Before Baseline 2 and before language systems are built for 2028.
Paper, no-ID, telephone, and other self-response options | Maintain multiple response pathways while testing paper-on-request, improved no-ID response, QR codes, CQA, and other enhancements. | Make direct participation easier and accommodate different access and trust needs. | Digital-first approaches can disadvantage people with limited broadband, accessibility needs, low digital literacy, shared devices, or distrust of online government systems. | A technically multimode census becomes practically digital-first, pushing harder-to-reach households into follow-up. | Test response modes by population, accessibility need, language, and geography. | Preserve low-barrier paper, telephone, no-ID, and accessible response; advertise alternatives clearly from first contact. | Before 2028 Dress Rehearsal contact materials and systems are finalized.
Continuous address updating | Maintain the address frame continuously using administrative data, imagery, geographic information, and targeted field verification instead of a single nationwide canvass. | Identify changes earlier, reduce expensive nationwide fieldwork, and focus verification on uncertain areas. | Informal housing, rural and remote residences, tribal areas, new construction, and hidden units may be less visible in automated sources. | An apparently complete frame systematically excludes housing that does not appear in standard administrative and commercial datasets. | Compare address-frame error under continuous updating and traditional field verification by community type. | Preserve robust local review and field verification; publish differential address-quality measures and criteria for targeted canvassing. | Before final address-review and field-verification plans for 2028–29.
Group quarters and special living situations | Expand specialized frames, administrative information, and possible self-response while integrating some operations more closely with broader census systems. | Improve facility lists, reduce dependence on a single administrator, and create more direct response opportunities. | Facility records may misstate characteristics or residence; specialized populations may be poorly served by generalized procedures. | Institutions supply incomplete data, direct participation is limited, and specialized situations are processed through procedures that do not fit them. | Test separately across correctional, college, military, shelter, outdoor, confidential, and other living situations. | Preserve specialized protocols and direct response where feasible; require separate quality measures by group-quarters type. | Before 2028 Dress Rehearsal design; some specialized tests must occur earlier.
Targeted field contact and smaller field infrastructure | Use models and administrative data to guide contact strategy, cross-train workers, and operate with fewer physical offices and more centralized support. | Concentrate effort, improve worker productivity, and reduce unnecessary visits and facilities. | Models may reduce effort in communities where contact is harder; centralized systems may weaken local knowledge and responsiveness. | Census saves money by withdrawing field capacity from households that require the most intensive effort to count accurately. | Compare field effort, contact success, and quality by population and geography under alternative strategies. | Establish minimum meaningful contact standards; preserve local and multilingual capacity; report differential field outcomes. | Before field requirements and staffing models are fixed for the Dress Rehearsal.
Coverage Estimation redesign | Replace the traditional PES structure with a broader system combining administrative data, independent field interviews, matching, and statistical estimation. | Expand measurement, potentially improve timeliness and substate information, and target expensive interviews. | Shared administrative sources may cause the census and its quality measure to miss the same people. | Census and Coverage Estimation agree because both rely on the same incomplete evidence, concealing systematic undercounts. | Quantify correlated errors and determine the amount of truly independent field data needed. | Require meaningful methodological independence and probability-based checks of apparent administrative agreement. | Before Coverage Estimation design enters the 2028 Dress Rehearsal.
Disclosure avoidance | Replace or redesign the planned 2030 system to comply with the Commerce prohibition on noise infusion, likely using some combination of coarsening, suppression, or other methods. | A new approach could address legitimate concerns about 2020 data utility while continuing to protect confidentiality. | Small populations and local geographies are most vulnerable to disappearing through aggregation or suppression. | Census protects confidentiality by eliminating enough demographic and geographic detail that important communities become unusable or invisible in public data. | Produce realistic demonstration products comparing privacy and utility across permissible approaches. | Revise or seek an exception to the DAO; require a public replacement plan, utility standards, independent review, and early demonstration data. | Replacement research plan immediately; method and product design before 2028 demonstration and Dress Rehearsal.
Redistricting data | Continue producing P.L. 94-171 data, subject to final race and ethnicity content, geography, disclosure avoidance, and release procedures. | Preserve a common national factual base for redistricting and voting-rights analysis. | Reduced racial, ethnic, voting-age, or block-level detail could make small communities difficult to identify and analyze. | Census technically provides required counts while withholding enough demographic detail to undermine practical redistricting and civil rights uses. | Test proposed disclosure rules and content against actual congressional, state, and local redistricting needs. | Define minimum P.L. 94-171 utility requirements; prefer simultaneous access and transparent release rules. | Before final disclosure and product specifications; well before April 1, 2031 release.
Communications and partnerships | Continue a national communications and community-partnership program, although formal advisory committees have been eliminated and major communications procurement remains unclear. | Trusted local messengers can increase self-response, explain census procedures, and identify emerging barriers. | Organizations may have less funding, capacity, or willingness to promote a census whose policies they cannot confidently defend. | Census needs community trust more than in 2020 but invests later or less while language, data-use, or content decisions make participation harder to promote. | Assess partner funding, staffing, trust, geographic gaps, and willingness to participate under current policy conditions. | Rebuild formal engagement mechanisms; clarify communications procurement; engage and resource trusted messengers early. | Partnership infrastructure should expand before 2028 and be fully operational well before 2030 outreach.
Enterprise IT and cloud infrastructure | Rely more heavily on shared Census systems, cloud services, contractors, and reusable enterprise technology. | Reduce duplicative development, enable earlier testing, improve scalability, and lower lifecycle cost. | Systemwide failures or competing enterprise priorities may affect decennial operations; concentrated linked data increase the consequences of misuse or breach. | A cyberattack, vendor failure, funding disruption, or tightly coupled system prevents Census from adapting during the short enumeration window. | Assess resilience, decennial service guarantees, access controls, contractor dependencies, and contingency plans. | Require credible continuity planning and heightened safeguards for linked person-level data, particularly the PCF. | Before enterprise dependencies are locked into 2028 integration and production contracts.
Funding and procurement efficiencies | Reduce costs through fewer field activities, shared infrastructure, automation, centralized operations, and enterprise acquisitions. | Lower costs and redirect resources toward activities that improve count quality. | Budget savings may be achieved by reducing precisely the staff, outreach, or field effort needed in communities that are hardest to enumerate. | Funding assumptions fail late and Census responds by cutting fieldwork, languages, communications, or quality control when there is no time to rebuild capacity. | Link projected savings to measurable quality outcomes and model contingency requirements. | Require transparent lifecycle costs, savings assumptions, procurement milestones, and contingency funding. | Annual appropriations cycle, with heightened scrutiny before 2028 and 2030 peak funding.
Technical rules beneath the Operational Plan | Translate broad commitments into internal requirements, thresholds, algorithms, workflows, and specifications as the design matures. | Allow Census to refine methods through research and testing without prematurely freezing the design. | Consequential decisions may become embedded in systems before affected communities know what the rules are. | Public plans remain reassuringly high-level while the real census is decided internally; by disclosure, changing it is considered operationally impossible. | Map requirements, decision memoranda, tests, and research findings to major operational choices. | Require progressive transparency: publish consequential rules when they begin driving requirements, procurement, or development. | Continuously, but especially before Baseline 2 and before major 2028 system builds.
Testing and design lock-in | Use small-scale research, the reduced 2026 Census Test, and the 2028 Dress Rehearsal to mature the design through Baselines 2 and 3. | Identify operational failures before production and allow evidence to improve the final design. | Current test sites do not cover many populations and conditions central to historically undercounted communities. | Testing confirms that integrated systems function without ever adequately testing whether they work for the populations most at risk. | Develop targeted tests for tribal, language, rural, group-quarters, mobility, administrative-record, and accessibility issues. | Publish predetermined metrics, community-specific results, unfavorable findings, and a research-to-decision crosswalk. | Alternative testing plan before Baseline 2; consequential unresolved issues before the 2028 Dress Rehearsal.
Documentation and archiving | Preserve operational records, paradata, planning materials, and permanent records through Census archiving and federal records processes. | Allow later scientific evaluation, litigation, congressional oversight, and planning for 2040. | Automated and continuously changing systems may make decisions impossible to reconstruct unless version histories and audit trails are deliberately retained. | Census can report the final result but cannot determine which rule, model, data source, or leadership decision produced a challenged outcome. | Identify the minimum records needed to reconstruct household-level and system-level decisions. | Adopt a 2030 auditability plan covering model versions, rules, data sources, contact histories, interventions, decisions, and rejected alternatives. | Before production systems begin overwriting or discarding operational history.